## Summary
WholeCart – Test Summary
Project | WholeCart B2B marketplace – Phase 1
Specification | Functional design v1.0 (WC-FDD-1.0-641d)
Environment | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS
Accounts used | buyer1 (Spice Route Kitchen), buyer2 (Café Dosa Corner), seller1 (WholeCart Direct), operator
Test date | 2026-10-14
Overall
Item | Count
Test cases
Passed
Failed
Pass rate
Defects logged
Defects open
Test execution by module
Module | Total | Pass | Fail | Pass % | Defects
Login & Access
Catalogue & Search
Cart
Checkout
Delivery Slots
Order History
Cancellation
Slot Change
Redelivery
Reorder
Refunds & Exchanges
Invoices
Monthly Statements
Inquiries
Seller - Orders
Seller - Products
Seller - CSV Import
Operator
Total
Test cases by user type
User type | Total | Pass | Fail
Buyer
Buyer, Operator
Buyer, Seller
Seller
Operator
Defects by severity and priority
Severity | High | Medium | Low | Total
Critical
Major
Minor
Trivial
Total
Defects by module
Module | Defects
Catalogue & Search
Cart
Checkout
Order History
Cancellation
Slot Change
Reorder
Invoices
Monthly Statements
Inquiries
Seller - Orders
Seller - Products
Seller - CSV Import
Operator
Key defects (Critical and Major)
Defect ID | Summary | Severity | Priority | Module
DEF-001 | Monthly statement includes a cancelled order and charges it in Amount due | Critical | High | Monthly Statements
DEF-009 | Seller cancellation is not shown to the buyer (BR-12) | Critical | High | Cancellation
DEF-006 | Category filter is ignored when combined with search text | Major | High | Catalogue & Search
DEF-010 | Minimum order per seller not enforced in a multi-seller checkout (BR-04) | Major | High | Checkout
DEF-011 | Default 'Minimum order per seller' is ₹2,000; design says ₹1,500 (BR-04) | Major | High | Checkout
DEF-014 | Message seller button does nothing | Major | High | Inquiries
DEF-015 | Reorder drops a line from the order without telling the buyer | Major | High | Reorder
DEF-016 | Out-of-stock products are displayed in the catalogue and search results | Major | High | Catalogue & Search
DEF-018 | Duplicate orders created and stock deducted twice on repeated order submission | Major | High | Checkout
DEF-019 | Updated same-day cut-off time in operator settings is not reflected at checkout | Major | High | Operator
DEF-020 | CSV import accepts negative stock and blank category without reporting errors | Major | High | Seller - CSV Import
DEF-021 | Logistics export shows slot end before slot start | Major | High | Operator
DEF-022 | Invoice is missing the delivery fee line and seller GSTIN | Major | High | Invoices

## Testcases
Test Case ID | Module | User Type | Test Case Title | Test Case Description | Test Case Type | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Application Environment | Status | Priority | Bug ID
TC-01-01 | Login & Access | Buyer | Buyer logs in with valid credentials | Verify buyer login with valid credentials. | Positive | App URL reachable | 1. Open /login 2. Enter username and password 3. Click Log in | buyer1 / Test@123 | Buyer should be logged in and taken to the Catalogue. Header should show 'Spice Route Kitchen' and a Log out link. | Login works. Buyer header shows 'Spice Route Kitchen'; seller login shows 'WholeCart Direct'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-01-02 | Login & Access | Buyer | Buyer cannot open another buyer's order (BR-21) | Verify a buyer cannot see another buyer's orders. | Negative | buyer2 has an order; note its id (e.g. /orders/7) | 1. Log in as buyer1 2. Open buyer2's order URL /orders/{id} 3. Try the same for /invoices/{id} | buyer1, buyer2 order id | Access should be denied (403/404). No order, invoice or statement details of the other buyer should be shown. | Access was denied. No order, invoice or statement details of the other buyer were shown. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-02-01 | Catalogue & Search | Buyer | Out-of-stock products never shown (BR-02) | Verify out-of-stock products are hidden from the catalogue. | Negative | Logged in as buyer1; seller1 (WholeCart Direct) products SKU-0030 and SKU-0047 have stock 0 | 1. As seller1, open Products and note SKU-0030 and SKU-0047 have stock 0 2. As buyer1, open Catalogue 3. Search SKU-0030, then SKU-0047 4. Open the product page | SKU-0030 Spice Toor Dal (stock 0), SKU-0047 Prime Moong Dal (stock 0) | The product should not appear in the catalogue list, in search results or under its category. The product count should not include it. | SKU-0030 Spice Toor Dal and SKU-0047 Prime Moong Dal have 0 stock but still appear in catalogue search. The product page shows 'In stock: 0 pieces' with Add to cart enabled. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-016
TC-02-02 | Catalogue & Search | Buyer | Category filter combined with search text | Verify search text and category filter work together. | Positive | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Type search text 2. Select category 3. Click Search | Chef + Oils | Only products matching both the search text and the selected category should be shown (e.g. Chef's Coconut Oil, Chef's Mustard Oil). The product count should match the list. | Search 'Chef' with category 'Oils' still showed 28 products from all categories. Needs re-check. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-006
TC-03-01 | Cart | Buyer | Quantity control is a dropdown 1-20 (5.1) | Verify the cart quantity control is a 1-20 dropdown. | Positive | Cart has one line | 1. Open Cart 2. Inspect Quantity control | - | Quantity should be a dropdown with values 1 to 20. Changing it should update the line total and net total immediately. | Quantity is a text box with an Update button, not a dropdown. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Medium | DEF-004
TC-03-02 | Cart | Buyer | Quantity boundaries per line 1 and 99 (BR-03) | Verify cart line quantity limits of 1 and 99. | Boundary | Cart has a line; product stock >= 99 units | 1. Set qty 1 -> accepted 2. Set qty 99 (via product page) -> accepted 3. Set qty 100 -> rejected | 1, 99, 100 | Quantities 1 and 99 should be accepted. Quantity 100 should be rejected with a clear message, and the line should stay unchanged. | Quantities 1 and 99 were accepted. Quantity 100 was rejected with a message, and the line stayed unchanged. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-03-03 | Cart | Buyer | Cannot add more pieces than in stock (BR-01) | Verify a buyer cannot order more than the available stock. | Negative | Logged in as buyer1; SKU-0007 Pure Basmati Rice has 1 piece in stock (case of 12) | 1. Open SKU-0007 Pure Basmati Rice 2. Choose Case, quantity 1 (12 pieces) 3. Click Add to cart | SKU-0007 Pure Basmati Rice: stock 1 piece, case of 12 (try 1 case); SKU-0012 Farm Basmati Rice: stock 3, case 24 | The add should be rejected with a 'not enough stock' message. The cart should never hold more pieces than are in stock. | Adding more than the available stock of the Test Data products was rejected with a 'not enough stock' message. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-01 | Checkout | Buyer | One summary row per seller plus grand total (5.2) | Verify checkout shows a summary per seller and a grand total. | Positive | Cart has items from FreshFarm Foods and WholeCart Direct | 1. Proceed to checkout | FreshFarm: Cardamom x2 case; WholeCart Direct: Butter case, Banana Chips case | There should be one row per seller showing Net, Tax, Delivery (incl. tax) and Total. Grand total should equal the sum of the seller totals. | One row per seller (FreshFarm ₹2,552.32, WholeCart Direct ₹2,004.82). Grand total ₹4,557.14 is correct. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-02 | Checkout | Buyer | Tax per rate on summed net, rounded half-up once per rate (BR-07) | Verify tax is calculated and rounded per tax rate. | Positive | Seller sub-order with 5% and 18% lines | 1. Add lines 2. Open checkout 3. Recalculate tax by hand | Butter case ₹692.76 (5%) + Banana Chips case ₹982.56 (18%) | Tax should be calculated on the total net of each tax rate and rounded half-up once per rate. For Butter (5%) and Banana Chips (18%), tax should be ₹34.64 + ₹176.86 = ₹211.50. | Tax is correct. Example: ₹1,584.24 at 5% shows ₹79.21 (rounded once, as required). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-03 | Checkout | Buyer | Delivery fee ₹118 when seller net below ₹3,000 (BR-08) | Verify the ₹118 delivery fee below ₹3,000 per seller. | Positive | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Checkout with seller net ₹2,318.40 | - | A delivery fee of ₹118.00 (₹100 + 18% tax) should be charged for each seller whose net is below ₹3,000. | ₹118 fee charged when seller net is below ₹3,000; no fee above ₹3,000. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-04 | Checkout | Buyer | No delivery fee at net exactly ₹3,000.00 and above | Verify no delivery fee at ₹3,000 and above. | Boundary | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Build seller nets ₹2,999.99 / ₹3,000.00 / ₹3,000.01 2. Check fee | 2999.99, 3000.00, 3000.01 | Delivery fee should be ₹118.00 at ₹2,999.99. It should be ₹0.00 at ₹3,000.00 and above. | Delivery fee was ₹118.00 below ₹3,000 (e.g. ₹2,240.00 net) and ₹0.00 at exactly ₹3,000.00 net (Almond Oil 2 pieces, WC-01028-1) and above. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-05 | Checkout | Buyer | Seller net below ₹1,500 blocks checkout (BR-04) | Verify checkout is blocked below the minimum order. | Negative | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Cart with one seller net ₹1,499.99 2. Place order | WholeCart Direct net ₹1,385.52 (Chef's Cumin Seeds 1 case) | The order should not be placed. The message should name the seller and state the ₹1,500 minimum. | Order is blocked, but the message says the minimum is ₹2,000 instead of ₹1,500. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-011
TC-04-06 | Checkout | Buyer | Seller net exactly ₹1,500.00 allowed | Verify an order of exactly the minimum is allowed. | Boundary | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Cart with seller net ₹1,500.00 2. Place order | Seller net ₹1,500.00. 'Minimum order per seller' setting was ₹1,000 at the time of testing (default ₹2,000, see DEF-011). | The order should be placed successfully at exactly ₹1,500.00 net. | The order was placed successfully at ₹1,500.00 net. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-07 | Checkout | Buyer | Minimum checked per seller, not on the whole cart | Verify the minimum order is checked for each seller. | Negative | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Seller A net ₹3,000, seller B net ₹500 2. Place order | WC-01010: WholeCart Direct net ₹132.48 (Chef's Chana Dal 1 case) + Coastal Beverages ₹11,887.32 | Checkout should be blocked when any one seller is below the minimum, even if the cart total is above it. The message should name that seller. | Order WC-01010-1 was placed with only ₹132.48 for WholeCart Direct, below the minimum. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-010
TC-04-08 | Checkout | Buyer | Order split into one sub-order per seller with numbers WC-xxxxx-n (BR-09) | Verify one sub-order is created per seller. | Positive | Cart with two sellers | 1. Choose valid date and slot 2. Place order | Delivery 2026-10-15 08:00-11:00 | One sub-order should be created per seller, numbered with the same checkout number plus seller index (e.g. WC-01008-1, WC-01008-2). | Two orders created: WC-01008-1 (WholeCart Direct) and WC-01008-2 (FreshFarm Foods). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-09 | Checkout | Buyer | Success message and redirect (5.2) | Verify the order confirmation message and redirect. | Positive | Valid cart, date and slot | 1. Place order | - | Buyer should be taken to Order history. Message should read 'Your order has been placed. Order number: WC-01008-1, WC-01008-2'. | Goes to Order history, but the message is only 'Order placed!' with no order numbers. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Medium | DEF-003
TC-04-10 | Checkout | Buyer | Cart is emptied after successful order | Verify the cart is emptied after an order is placed. | Positive | Order just placed | 1. Open Cart | - | The cart should be empty after the order is placed. | Cart is empty after placing an order. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-04-11 | Checkout | Buyer | Double submit creates one order (BR-10) | Verify a double-click on Place order creates one order. | Negative | Logged in as buyer1; cart has SKU-910 Almond Oil, 2 pieces | 1. Proceed to checkout and choose a valid date and slot 2. Double-click Place order 3. Check Order history and the product stock | SKU-910 Almond Oil, 2 pieces (stock 30) | Only one order should be created. Order history should show one set of sub-orders, and stock should be reduced only once. | Double-clicking Place order created two orders (WC-01028-1 and WC-01029-1, both ₹3,150.00). Stock dropped from 30 to 26, so it was deducted twice. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-018
TC-04-12 | Checkout | Buyer | Two buyers ordering the last stock at the same time (BR-01) | Verify stock is not oversold when two buyers order together. | Negative | Product stock 6 pcs; buyer1 and buyer2 each have 1 case (6 pcs) in cart | 1. Both place order at the same moment (parallel requests) | buyer1, buyer2 | Only one order should succeed. The other buyer should get a 'not enough stock' message, and stock should never go below zero. | Only one order succeeded. The other buyer got a 'not enough stock' message, and stock did not go below zero. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-05-01 | Delivery Slots | Buyer, Operator | Delivery date allowed today to today+7 (BR-05) | Verify delivery date is limited to today to today+7. | Boundary | Logged in as buyer1 (Spice Route Kitchen) / Test@123; Operator has fixed the store clock (BR-24) to the time given in Test Data | 1. Pick today, today+7, today+8, yesterday 2. Show slots / place order | Clock 2026-10-14 09:00 | Dates from today to today+7 should be allowed. Yesterday and today+8 should be rejected with a clear reason. | Today+8 (22/10/2026) is blocked with 'Delivery date must be within 7 days'. Dates within 7 days are allowed. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-05-02 | Delivery Slots | Buyer | Same-day morning slots always disabled with reason (BR-06) | Verify same-day morning slots are disabled. | Negative | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Choose today 2. Show slots | Today | For today, the 08:00-11:00 and 11:00-14:00 slots should be disabled with the reason shown. | Morning slots for today are disabled with a reason shown. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-05-03 | Delivery Slots | Buyer, Operator | Same-day slots disabled at and after cut-off 10:00 | Verify same-day slots close at the 10:00 cut-off. | Boundary | Operator has fixed the store clock (BR-24) to the time given in Test Data | 1. Choose today 2. Show slots 3. Try to post order with 14:00-17:00 anyway | Clock 10:00:00 and 10:48 | From 10:00, today's 14:00-17:00 and 17:00-20:00 slots should be disabled with the reason shown. A forced request should also be rejected by the server. | After 10:00, today's afternoon and evening slots are disabled with 'Same-day orders must be placed before 10:00'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-05-04 | Delivery Slots | Buyer | Slot full after 5 orders (BR-05) | Verify a slot closes after 5 orders. | Boundary | 4 orders already in 2026-10-16 08:00-11:00 | 1. Place 5th order in slot -> OK 2. Try 6th order in same slot | Capacity 5 | The 5th order should be accepted. After that the slot should show as full and a 6th order should be rejected. | The 5th order was accepted. The slot then showed as full, and a 6th order was rejected. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-06-01 | Order History | Buyer | Cancelled orders stay listed with status Cancelled (BR-11) | Verify cancelled orders stay in Order history. | Positive | One order cancelled | 1. Open Orders | WC-01008-1 | The cancelled order should stay in Order history with status 'Cancelled' and its original total. | Cancelled order WC-01008-1 stays in Order history with status 'cancelled'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-06-02 | Order History | Buyer | Only actions valid for the status are shown | Verify order detail shows only valid actions for its status. | Negative | Orders in placed, cancelled, delivered status | 1. View each order | - | Cancel should show only for placed/accepted orders within 5 minutes. Redelivery should show only after a failed delivery. Refund/exchange should show only for delivered orders. Cancelled orders should show only Reorder. | Cancelled, placed and delivered orders still show Cancel, Change slot, Redelivery and Refund buttons. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Medium | DEF-005
TC-06-03 | Order History | Buyer | Money shown in rupee format with thousands separator | Verify amounts use a thousands separator. | Positive | - | 1. Compare amounts with FDD mock-ups | - | All amounts should be shown with a thousands separator, e.g. ₹2,552.32. | Amounts show as ₹2552.32 instead of ₹2,552.32. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Low | DEF-007
TC-07-01 | Cancellation | Buyer | Buyer cancels a placed order within 5 minutes | Verify a buyer can cancel within 5 minutes. | Positive | Order placed < 5 min ago | 1. View order 2. Cancel order | WC-01008-1 placed 10:48:58 | The order should be cancelled and its status should change to 'Cancelled'. It should stay in Order history, and its stock should be returned. | Order cancelled within 5 minutes; status changed to 'cancelled'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-07-02 | Cancellation | Buyer, Operator | Cancel at exactly 5:00 allowed, 5:01 rejected (BR-11) | Verify the 5-minute cancel boundary. | Boundary | Operator has fixed the store clock (BR-24) to the time given in Test Data | 1. Place order at T 2. Set clock T+5:00, cancel -> OK 3. New order, clock T+5:01, cancel | T = 2026-10-14 09:00:00 | Cancel at exactly 5 minutes 0 seconds should succeed. Cancel at 5 minutes 1 second should be rejected with the 'within 5 minutes' message. | Cancel at exactly 5 minutes succeeded. Cancel at 5 minutes 1 second was rejected with the 'within 5 minutes' message. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-07-03 | Cancellation | Buyer | Cancel after 5 minutes rejected | Verify cancel is rejected after 5 minutes. | Negative | Order placed > 5 min ago | 1. View order 2. Cancel order | WC-01007-1 placed 10:44:06, tried ~10:50 | Cancel should be rejected with the 'within 5 minutes' message, and the order status should stay unchanged. | Cancel after 5 minutes is rejected with 'Orders can only be cancelled within 5 minutes'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-07-04 | Cancellation | Buyer | Stock returned on cancellation | Verify stock is returned when an order is cancelled. | Positive | Stock S before order of 12 pcs | 1. Place order 2. Cancel 3. Check stock | - | Stock of every product in the cancelled order should go back to the level before the order. | Stock of every product in the cancelled order went back to the level before the order. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-07-05 | Cancellation | Buyer, Seller | Seller cancels; buyer sees Cancelled immediately (BR-12) | Verify a seller cancellation shows to the buyer immediately. | Positive | Placed order for seller2 | 1. seller2 cancels 2. buyer1 refreshes Orders | WC-01012-1 (accepted), WC-01010-1 (placed), WC-01009-1 cancelled by seller1 | The buyer should see status 'Cancelled' straight away in Order history and order detail. Stock should be returned. | Seller cancelled WC-01012-1 and WC-01010-1, but the buyer still sees them as 'accepted' and 'placed'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-009
TC-08-01 | Slot Change | Buyer | Buyer changes slot before shipping (BR-15) | Verify a buyer can change the delivery slot before shipping. | Positive | Order placed/accepted | 1. View order 2. Choose new date/slot 3. Change slot | 2026-10-16 14:00-17:00 | The new date and slot should be saved and shown in the order detail, Order history and the seller's order list. | The slot was changed to 2026-10-16 14:00-17:00 and shown in the order detail, Order history and the seller's order list. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-08-02 | Slot Change | Buyer | Slot form defaults to current delivery | Verify the slot form shows the order's current delivery. | Positive | Order delivery 2026-10-15 08:00-11:00 | 1. View order | - | The Change slot form should be pre-filled with the order's current delivery date and slot. | Form shows today's date (14/10/2026) instead of the order's delivery date (15/10/2026). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Low | DEF-008
TC-09-01 | Redelivery | Buyer | Request redelivery after failed delivery (BR-14) | Verify a buyer can request redelivery after a failed delivery. | Positive | Seller marked order 'delivery failed' | 1. Buyer views order 2. Choose new valid slot 3. Request redelivery | WC-01011-1 is now 'delivery_failed' (seller1 marked Fail) | The new slot should be saved and the status should change to 'redelivery requested'. The order should appear in the logistics export. | For WC-01011-1, the new slot was saved and the status changed to 'redelivery requested'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-10-01 | Reorder | Buyer | Reorder adds every line with the original quantity (BR-16) | Verify Reorder adds all lines with original quantities. | Positive | Cart empty; past orders delivered/placed | 1. Orders > Reorder on a past order 2. Open Cart | buyer1: WC-01008-2 (Chef's Cardamom 2 cases). buyer2: WC-01021-1 (Basmati Rice 27 + Almond seeds 5), WC-01001-1 (Spice Basmati Rice 1, Daily Toor Dal 1, Royal Moong Dal 3), WC-01003-1 (Fresh Orange Juice 2, Farm Orange Juice 1, Chef's Cold Coffee 2) | Every line of the past order should be added to the cart with the same quantity as the original order. | Quantities are correct, but the last line of the order is missing from the cart (Almond seeds, Royal Moong Dal, Chef's Cold Coffee). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-015
TC-10-02 | Reorder | Buyer | Reorder a multi-line order | Verify Reorder of an order with several lines. | Positive | Cart has Cardamom | 1. Reorder WC-01008-1 | Butter case x1, Banana Chips case x1 | All lines of the order should be added to the cart. Existing cart lines should be kept, and the message should show the correct number of items added. | WC-01001-1 and WC-01003-1 each had 3 lines; Reorder added only 2. The last line was missing. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-015
TC-11-01 | Refunds & Exchanges | Buyer | Refund/exchange only for delivered orders (BR-17) | Verify refunds and exchanges are allowed only for delivered orders. | Negative | Orders placed, shipped, cancelled | 1. Try Send request on each | - | Refund and exchange should only be possible for delivered orders. For placed, shipped and cancelled orders the form should be hidden or the request rejected. | Refund/exchange form is shown on placed and cancelled orders. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-005
TC-11-02 | Refunds & Exchanges | Buyer, Seller | Partial refund amount includes tax on refunded qty (BR-18) | Verify the partial refund amount includes tax. | Positive | Delivered order, Banana Chips case x2 | 1. Partial refund 1 case 2. Seller approves | WC-01007-1 (delivered): refund 1 case Chef's Banana Chips ₹982.56 @18% | Refund for 1 case of Banana Chips should be ₹982.56 + ₹176.86 tax = ₹1,159.42. | For WC-01007-1, the refund for 1 case of Chef's Banana Chips was ₹1,159.42 (₹982.56 + ₹176.86 tax). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-11-03 | Refunds & Exchanges | Buyer, Seller | Total refunded/exchanged per line never exceeds ordered qty | Verify refunds cannot exceed the ordered quantity. | Boundary | Delivered line qty 2 | 1. Partial refund 1 2. Exchange 1 3. Try another refund of 1 | qty 2 | Requests should be accepted until the ordered quantity is used up. Any request beyond it should be rejected. | For a line with quantity 2, requests were accepted up to 2. A further request was rejected. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-12-01 | Invoices | Buyer | Invoice lines, tax by rate, delivery line and total = order total | Verify invoice content and total. | Positive | Logged in as buyer1; a delivered order with a delivery fee (seller net below ₹3,000) | 1. Orders > View WC-01040-1 2. Click Invoice 3. Check seller and buyer details, lines, tax by rate, delivery fee line and total | INV-00045 / WC-01040-1: Chef's Coconut 1 case, net ₹2,240.00, tax 5% ₹112.00, delivery fee ₹118.00, total ₹2,470.00 | Invoice should show seller and buyer details, every line, tax by rate, the delivery fee as its own line, and a total equal to the order total. | Invoice INV-00045 (WC-01040-1) has no delivery fee line and no seller GSTIN. The Total ₹2,470.00 is shown in very faint text and is hard to read. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-022, DEF-024
TC-13-01 | Monthly Statements | Buyer | Statement lists only orders delivered in the month (BR-20) | Verify the statement lists only delivered orders. | Positive | Placed, cancelled and delivered orders in Oct 2026 | 1. Statements > October 2026 > Show | October 2026 statement; WC-01008-1 (cancelled, ₹2,004.82) | Only orders delivered in that month should be listed. Amount due should equal their total minus approved refunds. | The October statement lists cancelled order WC-01008-1 (₹2,004.82), so it does not list only delivered orders. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-001
TC-13-02 | Monthly Statements | Buyer | Cancelled orders excluded from statement (BR-20) | Verify cancelled orders are not on the statement. | Negative | WC-01008-1 cancelled, never delivered | 1. Statements > October 2026 > Show | WC-01008-1 ₹2,004.82 | Cancelled order WC-01008-1 should not be listed. Orders total and Amount due should be ₹0.00. | Cancelled order WC-01008-1 is on the statement and ₹2,004.82 is added to Amount due. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-001
TC-13-03 | Monthly Statements | Buyer, Seller | Approved refunds deducted; rejected/pending not deducted | Verify only approved refunds reduce the statement. | Positive | Delivered order with 1 approved and 1 rejected refund | 1. Show statement | - | Only approved refunds should be deducted. Rejected and pending requests should not change the Amount due. | Only approved refunds were deducted. Rejected and pending requests did not change the Amount due. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-14-01 | Inquiries | Buyer | Buyer sends inquiry about an order | Verify a buyer can message the seller about an order. | Positive | Order exists | 1. Orders > Message seller 2. Type and send | WC-01023-1 (WholeCart Direct, cancelled) and any other order in Order history; message 'Please deliver before 10am' | Clicking 'Message seller' should open a message form. The message should be sent and the seller of that order should receive it. | Clicking 'Message seller' does nothing. No form opens. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Medium | DEF-014
TC-15-01 | Seller - Orders | Seller | Seller sees only own sub-orders | Verify a seller sees only their own orders. | Positive | Checkout with seller1 and seller2 items | 1. seller2 opens Orders | WC-01010 (seller1 sub-order -1, Coastal Beverages -2) | Seller should see only their own sub-order (WC-01010-1) and not the other seller's (WC-01010-2). | Seller sees only their own orders (WC-01010-1, not WC-01010-2). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-15-02 | Seller - Orders | Seller | Only valid actions per status (BR-13) | Verify seller actions match the order status. | Positive | Logged in as seller2 (FreshFarm Foods) / Test@123 | 1. Check buttons for placed, accepted, shipped, delivery failed, redelivery requested, delivered, cancelled | - | Placed should show Accept and Cancel; accepted should show Ship and Cancel; shipped should show Deliver and Fail; redelivery requested should show Ship; delivered and cancelled should show none. | Correct buttons for each status: placed (Accept, Cancel), accepted (Ship, Cancel), shipped (Deliver, Fail), delivered/cancelled (none). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-15-03 | Seller - Orders | Seller | Accept then ship then deliver | Verify the seller order flow Accept, Ship, Deliver. | Positive | Logged in as seller2 (FreshFarm Foods) / Test@123 | 1. Accept 2. Ship 3. Deliver | WC-01007-1 | Status should change at each step and the buyer should see the same status. An invoice should be issued when the order is delivered. | Order moved from accepted to shipped to delivered. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-15-04 | Seller - Orders | Seller | Seller order list Actions column aligned with rows | Verify the seller Orders table is aligned in every column. | Positive | Logged in as seller1 (WholeCart Direct); orders in placed, accepted, delivered, cancelled and delivery_failed status | 1. Log in as seller1 2. Open Orders 3. Compare the Actions column with the other columns for rows with and without buttons | seller1 Orders list: WC-01027-1 (delivered), WC-01026-1 (cancelled), WC-01025-1 (delivery_failed), WC-01028-1 (accepted) | Every row should have the same height across all columns. Row lines in the Actions column should line up with the rest of the table, also for rows with no buttons. | Rows with no buttons (delivered, cancelled, delivery_failed) are out of line in the Actions column; the row lines there do not match the other columns. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Low | DEF-023
TC-16-01 | Seller - Products | Seller | Seller product list pagination stops at last page | Verify product list paging stops at the last page. | Negative | Logged in as seller1 (WholeCart Direct) | 1. Products 2. Click Next until the last product (SKU-9005) is shown 3. Click Next again | - | Next should be hidden or disabled on the last page. An empty page should never be shown. | Clicking Next on the last page opens an empty page. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Low | DEF-012
TC-17-01 | Seller - CSV Import | Seller | Import valid UTF-8 CSV creates/updates products by SKU (IF-01) | Verify CSV import creates and updates products. | Positive | Logged in as seller2 (FreshFarm Foods) / Test@123 | 1. Upload CSV with 2 new SKUs and 1 existing SKU | Sample file edited: SKU-9001..9005 (Hill Basmati Rice 5.5kg, Classic Cold Coffee 200ml->400ml, Village Ghee 1L->10L, ...) | New SKUs should be created and existing SKUs updated with no duplicates. Imported products should appear in the buyer catalogue. | 5 products imported with no errors. Re-import updated them without duplicates. Buyer could see and order them. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-17-02 | Seller - CSV Import | Seller | Each invalid row reported with line number and reason | Verify CSV import reports invalid rows. | Negative | Logged in as seller1 (WholeCart Direct) / Test@123 | 1. Products > download the Sample file 2. Edit a row: stock -30 and category left blank 3. Upload the CSV 4. Check the import message and error list | CSV rows SKU-910 Almond Oil and SKU-911 Almond powder: stock -30, category blank (one row per upload) | Valid rows should be imported. Every invalid row should be reported with its line number and reason, and no row should be dropped silently. | CSV rows with stock -30 and a blank category were accepted. The page showed 'Import complete: 1 rows, 0 errors' and no row error was reported. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-020
TC-17-03 | Seller - CSV Import | Seller | Upload with no file chosen | Verify Upload without a file shows a clear message. | Negative | Logged in as seller1 | 1. Products 2. Do not choose a file 3. Click Upload | - | A message such as 'Please choose a CSV file' should be shown, and nothing should be imported. | Shows 'CSV must have columns...' instead of asking to choose a file. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | Low | DEF-013
TC-19-01 | Operator | Operator | Export contains accepted, shipped and redelivery-requested orders only (IF-02) | Verify logistics export content and columns. | Positive | Logged in as operator / Test@123; orders exist in placed, accepted, delivered and cancelled status | 1. Logistics export > Run export now 2. Open the downloaded CSV 3. Check the rows, column order and slot times | Downloaded CSV: WC-01028-1 (accepted, delivery 15/10/2026 14:00-17:00, 2 pieces) | The export should contain only accepted, shipped and redelivery-requested orders, with columns in the order given in IF-02. | CSV downloads and runs every hour, and columns are in the right order. Only the accepted order WC-01028-1 is included. But its 14:00-17:00 slot is exported as slot_start 17:00 and slot_end 14:00 (swapped). | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-021
TC-19-02 | Operator | Operator | Operator views and saves marketplace settings | Verify the operator can save marketplace settings. | Positive | Logged in as operator / Test@123 | 1. Open Settings 2. Note current values 3. Change Cancellation window 5 -> 10 and Minimum order per seller 2000 -> 1000 4. Save settings 5. Reload | Defaults seen: cut-off 10:00, cancellation 5 min, 5 orders/slot, min order ₹2,000, free delivery from ₹3,000, fee ₹100, store clock Real time | Settings saved' should be shown and the new values should remain after reload. | Settings changed and saved; new values stay after reload. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-19-03 | Operator | Buyer, Operator | Changed cancellation window applies to buyers immediately (BR-23) | Verify a new cancellation window applies immediately. | Positive | Logged in as operator / Test@123; buyer1 has a placed order | 1. Operator sets Cancellation window 10 2. Without restart, buyer opens a placed order and clicks Cancel order 3. Place a new order and cancel it 7 minutes later | WC-01017-1 placed 12:32:13 (buyer1); new order for step 3 | The new 10-minute window should apply straight away. An order 7 minutes old should be cancellable; one older than 10 minutes should be rejected. | After changing the window to 10 minutes, the buyer's message changed to 'within 10 minutes' straight away. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-19-04 | Operator | Buyer, Operator | Changed minimum order applies at checkout immediately (BR-04, BR-23) | Verify a new minimum order applies immediately. | Boundary | Logged in as operator / Test@123 | 1. Operator sets Minimum order per seller 1000 2. Buyer checks out seller net ₹999.99 -> blocked 3. Buyer checks out seller net ₹1,000.00 -> allowed | Min order ₹1,000 (set at 13:22) | With the minimum set to ₹1,000, ₹999.99 should be blocked and ₹1,000.00 should be allowed. | With the minimum set to ₹1,000, ₹999.99 was blocked and ₹1,000.00 was allowed. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-19-05 | Operator | Buyer, Operator | Pilot OPS-14: buyer3 gets free delivery until 31 Oct 2026 | Verify pilot OPS-14 free delivery for buyer3. | Positive | Logged in as operator / Test@123; banner 'Active pilot OPS-14' shown on Settings | 1. Log in as buyer3; checkout one seller with net < ₹3,000 2. Log in as buyer1; same cart 3. Operator fixes store clock 2026-11-01 09:00; buyer3 checks out again 4. Reset clock to Real time | buyer3 (शर्मा भोजनालय), buyer1; seller net e.g. ₹2,252.16 | buyer3 should pay ₹0.00 delivery until 31 Oct 2026; buyer1 should still pay ₹118.00. From 1 Nov 2026 buyer3 should pay ₹118.00. | With seller net below ₹3,000, buyer3 paid ₹0.00 delivery fee and buyer1 paid ₹118.00. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Pass | High
TC-19-06 | Operator | Buyer, Operator | Changed same-day cut-off applies at checkout immediately (BR-06, BR-23) | Verify a new same-day cut-off time applies at checkout immediately. | Positive | Logged in as operator / Test@123 and as buyer1 (separate browser); buyer has items in cart | 1. Operator: Settings > change 'Same-day cut-off time' from 10:00 to 18:00 2. Save settings 3. Buyer: open Checkout and choose today's date 4. Click Show slots and check the 14:00-17:00 and 17:00-20:00 slots | Same-day cut-off time 18:00; delivery date 14/10/2026 (today) | Checkout should use the new cut-off straight away. Before 18:00, today's 14:00-17:00 and 17:00-20:00 slots should be available, and any message should mention 18:00. | After saving 18:00, today's 14:00-17:00 and 17:00-20:00 slots are still disabled with 'Same-day orders must be placed before 10:00'. | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Fail | High | DEF-019

## Bugs
Defect ID | Module | Bug Summary | Bug Description | Preconditions | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity | Priority | Evidence | Linked Test Cases | Environment | Status | Reported Date
DEF-001 | Monthly Statements | Monthly statement includes a cancelled order and charges it in Amount due | Cancelled orders should not be on the statement, but WC-01008-1 is listed and charged ₹2,004.82. | Logged in as buyer1 (Spice Route Kitchen) / Test@123; WC-01008-1 placed and cancelled within 5 minutes | 1. Place an order (WC-01008-1, ₹2,004.82) 2. Cancel it within 5 minutes 3. Statements > October 2026 > Show | WC-01008-1, ₹2,004.82, October 2026 | Cancelled orders should not appear on the statement. Orders total and Amount due should be ₹0.00 when no orders are delivered. | Cancelled order WC-01008-1 is listed on the October statement with status 'cancelled', and ₹2,004.82 is added to Orders total and Amount due. | Critical | High | evidence/DEF-001_statement_cancelled.mp4 | TC-13-01, TC-13-02 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-003 | Checkout | Order success message does not show order numbers | Message should include the order numbers; only 'Order placed!' is shown. | Logged in as buyer1 (Spice Route Kitchen) / Test@123; valid cart with 2 sellers | 1. Checkout, choose 2026-10-15 08:00-11:00 2. Place order | FreshFarm + WholeCart Direct cart | After placing an order the buyer should see 'Your order has been placed. Order number: WC-01008-1, WC-01008-2'. | Buyer is taken to Order history, but the message shows only 'Order placed!' without the order numbers. | Minor | Medium | evidence/DEF-003_order_placed_msg.mp4 | TC-04-09 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-004 | Cart | Cart quantity is a free-text box, not a 1-20 dropdown | Quantity should be a 1-20 dropdown; it is a text box with an Update button. | Logged in as buyer1 (Spice Route Kitchen) / Test@123; cart has lines | 1. Open Cart 2. Look at Quantity | - | Quantity should be a dropdown with values 1 to 20, and changing it should update the line straight away. | Quantity is a text box with a separate Update button, so any value can be typed. | Minor | Medium | evidence/DEF-004_cart_qty_textbox.mp4 | TC-03-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-005 | Order History | Order detail shows actions that are not valid for the status | Cancel, Change slot, Redelivery and Refund buttons show on cancelled, placed and delivered orders. | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Cancel WC-01008-1 2. View it 3. Click Cancel order again 4. Also view placed order WC-01007-1 | WC-01008-1 (cancelled), WC-01007-1 (placed), WC-01021-1 (delivered) | Each order should show only the actions valid for its status. Cancelled orders should show only Reorder, and Refund should show only on delivered orders. | Cancel order, Change slot, Request redelivery and Refund buttons are shown on cancelled, placed and delivered orders. Clicking Cancel on a cancelled order says 'This order can no longer be cancelled'. | Minor | Medium | evidence/DEF-005_cancelled_actions.mp4 | TC-06-02, TC-11-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-006 | Catalogue & Search | Category filter is ignored when combined with search text | Search 'Chef' + category 'Oils' still shows all categories. | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Catalogue 2. Search 'Chef', All categories -> 28 products 3. Select 'Oils', click Search | Chef + Oils | Only products matching both the search text and the category should be shown, and the count should match. | After searching 'Chef' with category 'Oils', the list still shows 28 products from Snacks, Grains, Dairy and Spices. | Major | High | evidence/DEF-006_category_filter.mp4 | TC-02-02 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-007 | Order History | Amounts shown without thousands separator | Amounts show as ₹2552.32 instead of ₹2,552.32. | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. Look at amounts on Cart, Checkout, Orders | - | Amounts should be shown with a thousands separator, e.g. ₹2,552.32. | Amounts are shown without a separator, e.g. ₹2552.32 on cart, checkout and Order history. | Trivial | Low | evidence/DEF-003_order_placed_msg.mp4 | TC-06-03 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-008 | Slot Change | Change-slot form pre-filled with today's date instead of the order's delivery date | Change slot form shows today's date, not the order's delivery date. | Logged in as buyer1 (Spice Route Kitchen) / Test@123 | 1. View order WC-01008-1 (delivery 2026-10-15 08:00-11:00) | - | The Change slot form should show the order's current delivery date and slot. | Change slot form shows today's date (14/10/2026) and 08:00-11:00 instead of the order's delivery date (15/10/2026). | Trivial | Low | evidence/DEF-005_cancelled_actions.mp4 | TC-08-02 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-009 | Cancellation | Seller cancellation is not shown to the buyer (BR-12) | Seller cancelled the order, but the buyer still sees 'accepted' / 'placed'. | seller1 and buyer1 logged in (separate browsers) | 1. seller1 cancels WC-01012-1 (accepted) and WC-01010-1 (placed) 2. buyer1 opens Orders and the order detail | WC-01012-1 (accepted), WC-01010-1 (placed) | When a seller cancels, the buyer should see 'Cancelled' immediately and the stock should be returned. | Seller's list shows WC-01012-1 and WC-01010-1 as 'cancelled', but the buyer still sees them as 'accepted' and 'placed'. Buyer's own Cancel fails with 'This order can no longer be cancelled'. | Critical | High | evidence/DEF-009_seller_view.mp4; evidence/DEF-009_buyer_view.mp4 | TC-07-05 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-010 | Checkout | Minimum order per seller not enforced in a multi-seller checkout (BR-04) | WC-01010-1 was placed with ₹132.48 net, below the per-seller minimum. | buyer1; cart with WholeCart Direct item below minimum + Coastal Beverages items above minimum | 1. Add Chef's Chana Dal 1 case (₹132.48, WholeCart Direct) 2. Add Coastal Beverages items (> ₹11,000) 3. Place order | WC-01010-1 net ₹132.48, WC-01010-2 ₹11,887.32 | Checkout should be blocked when any seller's net is below the minimum, and the message should name that seller. | Order WC-01010-1 for WholeCart Direct was placed with only ₹132.48 net (total ₹257.10), because the other seller in the same checkout was above the minimum. | Major | High | evidence/DEF-010_min_order_bypass.mp4 | TC-04-07 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-011 | Checkout | Default 'Minimum order per seller' is ₹2,000; design says ₹1,500 (BR-04) | Minimum order is set to ₹2,000; design says ₹1,500. | operator and buyer1 | 1. Operator: open Settings, read Minimum order per seller 2. Buyer: cart Chef's Cumin Seeds 1 case (₹1,385.52), place order | Setting ₹2,000; net ₹1,385.52 | The minimum order per seller should be ₹1,500 as per the design, so orders from ₹1,500 should be allowed. | Operator setting 'Minimum order per seller' is ₹2,000, and checkout shows 'Minimum order value is ₹2000 per seller'. | Major | High | evidence/DEF-011_checkout_min_2000.mp4 ; evidence/DEF-011_settings_min_2000.mp4 | TC-04-05 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-012 | Seller - Products | Product list Next link opens an empty page after the last page | Next on the last page opens an empty product list. | Logged in as seller1 | 1. Products 2. Click Next past the last page | - | Next should be hidden or disabled on the last page. | Clicking Next on the last page of the seller's product list opens an empty table with only Previous and Next links. | Minor | Low | evidence/DEF-012_products_empty_page.mp4 | TC-16-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-013 | Seller - CSV Import | Upload without a file shows a misleading column error | Upload with no file says 'CSV must have columns' instead of 'choose a file'. | Logged in as seller1 | 1. Products 2. Leave 'No file chosen' 3. Click Upload | - | The page should ask the seller to choose a CSV file. | With no file chosen, clicking Upload shows 'CSV must have columns: sku, name, category, ...'. | Trivial | Low | evidence/DEF-013_upload_no_file.mp4 | TC-17-03 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-014 | Inquiries | Message seller button does nothing | Clicking Message seller in Order history does nothing; no message form opens. | buyer1 logged in; Order history has orders | 1. Orders 2. Click 'Message seller' on WC-01023-1 3. Click it again | WC-01023-1 (WholeCart Direct) | Clicking 'Message seller' should open a message form, and the seller should receive the message. | Clicking 'Message seller' on WC-01023-1 several times does nothing: no form, no page change and no error. | Major | High | evidence/DEF-014_message_seller_no_action.mp4 | TC-14-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-015 | Reorder | Reorder drops a line from the order without telling the buyer | Reorder leaves out the last line of the order (seen on WC-01021-1, WC-01001-1, WC-01003-1) with no warning. Likely cause: lines that cannot be filled from current stock are dropped silently (Almond seeds: 20 pieces in WC-01021-1, only 12 in stock). | buyer2 logged in; cart empty | 1. Orders > View the order (note all lines) 2. Orders > Reorder the order 3. Open Cart and compare | WC-01021-1 (Basmati Rice 27, Almond seeds 5); WC-01001-1 (Spice Basmati Rice 1, Daily Toor Dal 1, Royal Moong Dal 3); WC-01003-1 (Fresh OJ 2, Farm OJ 1, Chef's Cold Coffee 2) | Every line of the order should be added to the cart. If a product cannot be added, the buyer should be told which one. | Reorder adds all lines except the last one, with no warning: Almond seeds (WC-01021-1), Royal Moong Dal (WC-01001-1) and Chef's Cold Coffee (WC-01003-1) were missing from the cart. | Major | High | evidence/DEF-015_reorder_missing_line.mp4; evidence/DEF-015_reorder_WC-01001.mp4; evidence/DEF-015_reorder_WC-01003.mp4 | TC-10-01, TC-10-02 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-016 | Catalogue & Search | Out-of-stock products are displayed in the catalogue and search results | Products with zero stock are still displayed in the buyer's catalogue and search results, and can be opened and added to the cart. | seller1 and buyer1 accounts / Test@123 | 1. Log in as seller1 and open Products 2. Note that SKU-0030 and SKU-0047 have stock 0 3. Log in as buyer1 and open Catalogue 4. Search SKU-0030, then SKU-0047 5. Open the product page | SKU-0030 Spice Toor Dal (stock 0), SKU-0047 Prime Moong Dal (stock 0) | Products with zero stock should not be displayed in the catalogue list, name/SKU search results, or category filter results. The total product count should exclude all out-of-stock products. | SKU-0030 Spice Toor Dal and SKU-0047 Prime Moong Dal have 0 stock in the seller's product list, but both appear in the buyer's catalogue search by SKU. The product page shows 'In stock: 0 pieces' with Add to cart enabled. | Major | High | evidence/DEF-016_out_of_stock_shown.mp4 | TC-02-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-018 | Checkout | Duplicate orders created and stock deducted twice on repeated order submission | The system creates duplicate sub-orders when the buyer double-clicks the Place order button, instead of processing the order only once. | Logged in as buyer1 | 1. Log in as a buyer and add an available product to the cart. 2. Proceed to checkout and enter the required details. 3. Note the available stock quantity. 4. Double-click the Place order button. 5. Verify the order history for duplicate orders or sub-orders. 6. Verify whether the stock was deducted more than once. | SKU-910 Almond Oil, 2 pieces (stock 30); orders WC-01028-1 and WC-01029-1 (₹3,150.00 each); stock 30 → 26 | The system should process the order only once, even if the buyer double-clicks the Place order button. Only one set of sub-orders should be created, and the stock should be deducted only once. | Double-clicking Place order created two orders, WC-01028-1 and WC-01029-1 (₹3,150.00 each, placed at the same time). Almond Oil stock dropped from 30 to 26, so it was deducted twice. | Major | High | evidence/DEF-018_double_click_duplicate_orders.mp4 | TC-04-11 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-019 | Operator | Updated same-day cut-off time in operator settings is not reflected at checkout | When the same-day delivery cut-off time is changed from 10:00 to 18:00 in Operator Settings, the updated time is not reflected in the checkout delivery slot options. The checkout continues to display the previous cut-off time instead of the updated configuration. | Operator and buyer1 accounts / Test@123 | 1. Log in as operator 2. Navigate to Operator Settings and change the same-day delivery cut-off time from 10:00 to 18:00. 3. Save the updated settings. 4. Log in as a buyer and add a product to the cart. 5. Proceed to checkout and navigate to the Delivery Slot section. 6. Verify the cut-off time displayed for the 14:00–17:00 and 17:00–20:00 delivery slots. | Operator: Same-day cut-off time 18:00 (saved). Buyer: checkout with delivery date 14/10/2026 (today) | The checkout delivery slot information should reflect the updated cut-off time of 18:00. Same-day delivery should be available only for the 14:00–17:00 and 17:00–20:00 slots when the order is placed before the configured cut-off time. | After saving 18:00, today's 14:00-17:00 and 17:00-20:00 slots are still disabled with 'Same-day orders must be placed before 10:00'. | Major | High | evidence/DEF-019_cutoff_setting_not_applied.mp4 | TC-19-06 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-020 | Seller - CSV Import | CSV import accepts negative stock and blank category without reporting errors | When a CSV row has a negative stock value (-30) or a blank category, the import is reported as successful with zero errors. Invalid rows should be rejected and reported with their line number and reason. | Logged in as seller1 | 1. Log in as seller and open My Products 2. Prepare a CSV with valid product details but stock -30 and the category left blank 3. Upload the CSV using the product import option 4. Check the import message and error count 5. Check whether the invalid row was imported and whether an error with line number and reason is shown | CSV rows SKU-910 Almond Oil and SKU-911 Almond powder: stock -30, category blank | Valid rows should be imported successfully. Each invalid row should be reported with its line number and reason, and no invalid row should be silently accepted or dropped. | Both uploads show 'Import complete: 1 rows, 0 errors'. The negative stock and blank category are not flagged or reported. | Major | High | evidence/DEF-020_csv_invalid_stock_accepted.mp4 | TC-17-02 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-021 | Operator | Logistics export shows slot end before slot start | The logistics export swaps slot start and end: an order with slot 14:00-17:00 is exported as slot_start 17:00 and slot_end 14:00. | Logged in as operator; at least one accepted/shipped order exists | 1. Logistics export 2. Click 'Run export now' 3. Open the downloaded CSV 4. Check slot_start and slot_end | Logistics export CSV: WC-01028-1 (accepted, delivery 15/10/2026 14:00-17:00, 2 pieces) | slot_start and slot_end should match the order's delivery slot: 14:00 and 17:00 for WC-01028-1. slot_end should always be after slot_start. | The CSV shows slot_start 17:00 and slot_end 14:00 for WC-01028-1, whose slot is 14:00-17:00. The start and end times are swapped. | Major | High | evidence/DEF-021_export_slot_times.mp4 | TC-19-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-022 | Invoices | Invoice is missing the delivery fee line and seller GSTIN | The invoice does not show the delivery fee as its own line and does not show the seller's GSTIN, both required by BR-19. | Buyer should have one delivered order | 1. Log in as buyer 2. Place an order below ₹3,000 net (delivery fee applies) 3. Log in as seller and deliver the order 4. Log back in as buyer 5. Orders > View the delivered order > click Invoice 6. Check the invoice lines and the seller details | INV-00045 / WC-01040-1: Chef's Coconut 1 case, net ₹2,240.00, tax ₹112.00, delivery fee ₹118.00 | The invoice should show the delivery fee (₹100 + 18% tax = ₹118.00) as its own line and the seller's GSTIN under the seller name (BR-19). Lines, tax and fee should add up to the total. | Invoice INV-00045 shows only the Chef's Coconut line (net ₹2,240.00, tax ₹112.00). There is no delivery fee line and no seller GSTIN, although the Total ₹2,470.00 includes the ₹118.00 fee. | Major | High | evidence/DEF-022_invoice_fee_missing_total_faded.png | TC-12-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-023 | Seller - Orders | Seller Orders page: Actions column not aligned with the rows | Actions column on the seller Orders page is out of line for rows without buttons. | Logged in as seller1; orders in different statuses | 1. Log in as seller1 2. Click Orders 3. Look at the Actions column for delivered, cancelled and delivery_failed rows | seller1 Orders list (WC-01027-1 to WC-01018-1) | Each row should line up across all columns, including the Actions column, whether or not the row has buttons. | For rows without buttons (delivered, cancelled, delivery_failed), the Actions column cells are shifted and their row lines do not match the other columns. | Minor | Low | evidence/DEF-023_seller_actions_alignment.png (screenshot, marked area) | TC-15-04 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14
DEF-024 | Invoices | Invoice total amount text is barely visible | On the invoice page, the Total amount is shown in very faint text and is hard to read. | Buyer should have one delivered order | 1. Log in as buyer 2. Orders > View a delivered order 3. Click the Invoice link 4. Look at the Total next to Net and Tax | INV-00045 / WC-01040-1 | The Total should be shown in clearly readable text, at least as visible as Net and Tax. | The Total ₹2,470.00 is shown in very light text on a white background and is almost invisible. | Minor | Low | evidence/DEF-022_invoice_fee_missing_total_faded.png | TC-12-01 | QA - http://13.200.185.1/c/purushoth-kumar-efaa03 ¦ Chrome, macOS | Open | 2026-10-14

## Questions & Assumptions
# | Area | Question for the product owner | Assumption used | Related
1 | Release notes | The design doc says approved changes after v1.0 are in the Release notes. Which v1.0 rules have changed? | Tested against design v1.0. Any defect that an approved release note covers (e.g. DEF-011) should be closed. | All
2 | BR-04 Minimum order | The app enforces ₹2,000 per seller by default; the design says ₹1,500. Which is correct? | ₹1,500 is the requirement (logged as DEF-011). | DEF-011, TC-04-05
3 | BR-04 Multi-seller checkout | If one seller in a checkout is below the minimum, should the whole checkout be blocked or only that seller's sub-order? | The whole checkout is blocked, with a message naming the seller. | DEF-010, TC-04-07
4 | BR-11 / BR-04 Operator settings | Operator settings let the cancellation window and minimum order be changed, but the design states them as fixed (5 minutes, ₹1,500). Are they meant to be configurable? | Yes, they are configurable (BR-23), but the design values are the defaults to test against. | TC-19-03, TC-19-04
5 | Pilot OPS-14 | The settings page shows 'buyer3 has free delivery until 31 Oct 2026'. This is not in the design. Does it waive the full ₹118 fee, and should the invoice show a ₹0 fee line? | buyer3 pays ₹0 delivery until 31 Oct inclusive; normal BR-08 rules apply from 1 Nov. | TC-19-05
6 | BR-16 Reorder and existing cart | Should Reorder add the past order's lines to items already in the cart, or replace the cart? | Lines are added to the existing cart, as BR-16 says 'adds every line… to the cart'. | TC-10-02
7 | BR-16 Reorder and stock | What should Reorder do when a line cannot be filled from current stock? | Add what it can and tell the buyer which line was skipped. | DEF-015
8 | BR-06 Cut-off boundary | Is an order at exactly 10:00:00 'before the cut-off'? | 09:59:59 is allowed; 10:00:00 is not. | TC-05-03
9 | BR-08 Fee boundary | Is the delivery fee charged at exactly ₹3,000.00 net? | No fee at ₹3,000.00 and above. | TC-04-04
10 | BR-05 Slot capacity | Is slot capacity counted per sub-order or per checkout, and does a cancelled order free its place? | Each sub-order counts as one order; cancelled orders free the place. | TC-05-04
11 | BR-17 / BR-18 Refunds | Is the delivery fee refunded on a full refund? Does a rejected request free its quantity for a new request? | The delivery fee is not refunded; a rejected quantity can be requested again. | TC-11-02, TC-11-03
12 | BR-20 Statement month | Is an order included by its delivery date, and is a refund deducted in the month it is approved? | Delivery date; refunds in the month approved. | TC-13-01
13 | BR-12 Seller cancellation | Can a seller cancel an order after the buyer's 5-minute window, and how is the buyer told? | Yes, for placed and accepted orders; the buyer must see Cancelled immediately. | DEF-009
14 | IF-01 CSV import | Must case_price equal piece_price × case_size? Is a duplicate SKU inside one file an error? | No price consistency check; a duplicate SKU in one file is reported as an error. | TC-17-01, TC-17-02
15 | Inquiries | 'Message seller' has no rules in the design (length, attachments, notifications). What is expected? | Plain-text message, one thread per order, visible only to that buyer and seller. | DEF-014
16 | Money format | Mock-ups show ₹2,436.40 but the app shows ₹2436.40. Is the separator required? | Yes, the mock-up format is the requirement (logged as DEF-007). | DEF-007